## UNT02
TSL Tool ID | DOWN CATEGORY | DOWN DATE | DOWN TIME | ISSUES / UPDATES | ACTION TAKEN | UP DATE | UP TIME | DOWN HOURS
UNT02 | CM | 2019-01-07 | 9:00 | facility shutdown | chamber isolated and turbos are turned off, UNT02 SMC chiller trip due to PCW temperature ramp up | 2019-01-10 | 12:00 | 75
UNT02 | PM | 2019-03-25 | 9:00 | Semi annual PM | PM completed and tool released | 2019-03-25 | 14:00 | 5
UNT02 | CM | 2019-06-22 | 15:30 | TC I/O board fail..need to reboot | found 5v PS fail,replaced and encountered -15v PS fail on P2 , | 2019-06-27 | 15:00 | 119.5
UNT02 | CM | 2019-06-27 | 9:00 | P2 polymer peel off issue and down for chamber PM | perform chamber cleaning and replaced swap kit, consumable cleaned and reused , tool released and CP fail issue ,open chamber wet clean done | 2019-06-27 | 20:00 | 11
UNT02 | CM | 2019-09-01 | 6:00 | Monitor screen black out fail issue | found digital panel fail..replaced used monitor ..issue fixed | 2019-09-02 | 11:00 | 29
UNT02 | CM | 2019-09-13 | 15:00 | PC2 cp fail issue | After replaced focus ring encounter cp fail issue and down for unschedule chamber PM , replaced cleaned swap kit and found new focus ring and insulator generate particulars , need new paryts. | 2019-09-17 | 13:00 | 94
UNT02 | CM | 2019-12-16 | 9:00 | P2 CP fail issue | exit | 2019-12-16 | 17:00 | 8
UNT02 | CM | 2020-02-10 | 14:00 | Transfer chamber dry pump oil degarded | Drain old oil and refilled and P1 drum lead screw greased, tool released | 2020-02-10 | 17:00 | 3
UNT02 | CM | 2020-02-16 | 19:00 | Smif A hang during UNloading | lot recovered and smif released | 2020-02-16 | 21:00 | 2
UNT02 | PM | 2020-03-18 | 12:00 | SAPM due | perform mainframe cleaning and indexer greasing done, Tool released for QC | 2020-03-18 | 17:00 | 5
UNT02 | CM | 2020-06-01 | 16:00 | PC 2 CP issue | Extended long purging done and CP passed. | 2020-06-02 | 10:00 | 18
UNT02 | PM | 2020-08-06 | 9:30 | PC2 RF PM and HDD backup. | Pm done replaced swap kit and consumables New touch disply replaced. Hdd Back up failed. Copier not detecting the HDD. while power on PC1 -15V power supply failed. Replaced new power supply and issue fixed. PC2 gap motor alarm. reset the servo drive and grasing done. under monitor | 2020-08-10 | 14:00 | 100.5
UNT02 | CM | 2020-08-14 | 20:00 | PC2 Gap motor alarm | gap motor overload error (servo driver is showing 7) tried to init but didnot help. removed and checked the motor and found it is faulty. swapped motor frm PC1 to PC2 and released. Pc1 waiting for motor. | 2020-08-17 | 15:00 | 67
UNT02 | CM | 2020-08-19 | 11:00 | PC2 Upper temp stabilization alarm | Increased the cooling air flow and released | 2020-08-19 | 12:00 | 1
UNT02 | CM | 2020-08-26 | 11:30 | PC2 upper temp stabilization error | Reboot the main frame also rest the temp board issue fixed under monitoring | 2020-08-26 | 12:00 | 0.5
UNT02 | CM | 2020-08-27 | 9:00 | LL IPX pump failed | Replaced with new EPX 180e pump and released | 2020-08-27 | 13:00 | 4
UNT02 | CM | 2020-09-03 | 14:00 | PC1 new gap motor replaced & Mini PM done | PC1 new gap motor installed and ch mini PM done (replaced nw focus ring and ring insulators 2) chamber released | 2020-09-17 | 15:00 | 337
UNT02 | CM | 2020-09-20 | 11:00 | PC1 process start timeout error | Adjsted CV pressure equal to CM pressure and issue fixed | 2020-09-20 | 11:30 | 0.5
UNT02 | PM | 2020-09-21 | 10:00 | Annual Pm Due | performed Smif pm and cleaned LL and Transfer chamber rlsd. | 2020-09-21 | 13:00 | 3
UNT02 | CM | 2020-09-22 | 11:00 | PC2 TEOS etch rate low issue | Mfc verication done for CHF3 and O2 MFC. no issue found. | 2020-09-22 | 12:00 | 1
UNT02 | CM | 2020-09-24 | 9:00 | LLA mech cp high | Loadlock cleaning done and released. | 2020-09-24 | 10:00 | 1
UNT02 | CM | 2020-09-26 | 10:00 | PC2 backside pressure alarm | recover the wafer and ran next wfr without issue | 2020-09-26 | 11:00 | 1
UNT02 | CM | 2020-10-07 | 16:00 | PC2 backside he alalrm & lift pin not in position alarm | Checked the sensor position found ok. open the chamber and verified the lift movenment.adjusted the lift pin position and relaed. Ran 35 wfrs afterthat same alarm. Suspect liftpin motor linear drive is faulty. part ordered from TSL | 2020-10-07 | 16:00 | 0
UNT02 | CM | 2020-11-04 | 9:00 | PC2 backside he alalrm & lift pin not in position alarm | Drain the chiller, open the chamber removed the ESC and lift pin. removed the lift pin connecting screw. Removed the RF match and gap cover, removed the pin motor mounting screw. replaced with new motor. and installed back lift pin and ESC. adjusted lift pin sensor position. and turn on chiller and verified the leak. robot teaching done. and Gap calibration done. chamber pump down inprogress | 2020-11-06 | 17:00 | 56
UNT02 | CM | 2020-11-07 | 16:00 | PC2 lift pin motor issue | Ch leak check passed. ran 25 wafers seasoning without issue. chamber released and QC passed | 2020-11-16 | 12:00 | 212
UNT02 | CM | 2020-12-07 | 9:00 | PC2 high CP fail issue | Chamber PM done and replaced consumables except focus ring. | 2020-12-08 | 11:00 | 26
UNT02 | CM | 2020-12-28 | 11:00 | PC1 CP failed | Opened chamber and cleaning done. Chamber released for QC | 2020-12-28 | 16:00 | 5
UNT02 | CM | 2021-01-24 | 18:00 | LLB cassette unload error | AGV and SMIF communication alarm cleared. Tool released. | 2021-01-25 | 10:00 | 16
UNT02 | PM | 2021-02-09 | 12:00 | PC2 Replace new focus ring | New focus ring replaced and chamber cleaning done. Post recovery done and tool released for seasoning and QC. | 2021-02-09 | 16:30 | 4.5
UNT02 | CM | 2021-03-22 |  | PC1 CP fail | Chamber purging done and released for seasoning and QC. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC2 CP fail | Chamber purging done and released for seasoning and QC. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC1 & PC2 CP fail | Both LL's cleaned and process chambers purging done. Tool released for QC. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC2 CP fail | After ran many seasoning wafers, CP passed. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC2 defects issue - down for PM | Chamber PM done and semi annual PM done. | 2021-03-22 | 9:30 | 9.5
UNT02 | CM | 2021-03-22 |  | Dry pump | All the dry pumps oil changed / top up done. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC2 Ash ER low | O2 MFC flow verification done. Released for QC. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC2 Ash ER low | Swapped O2 MFC with PC1. Verified gas flow and MFC. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC2 Ash ER low | RF Verification done. Releassed for QC. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC2 Ash ER low | Request to run "post PM recovery procedure" for sesoning and QC. | 2021-03-22 |  | 0
UNT02 | CM | 2021-03-22 |  | PC2 Ash ER low | Ash ER passed but TEOS ER failed on higher side. More seasoning wafers run ongoing | 2021-03-22 |  | 0
UNT02 | CM | 2021-06-24 | 10:00 | CC1 cassette exist error bef loading sequence | Adjusted cassette presence switch. Monitoring. | 2021-06-24 | 11:00 | 1
UNT02 | CM | 2021-07-01 | 10:30 | PC2 etch rate unstable & VIA Etch stop issue | PM done. Replaced process kits with cleaned kits. Focus ring cleaned and use back(RF hrs:34). post pm recovery done and rlsd. | 2021-07-02 | 10:30 | 24
UNT02 | CM | 2021-07-02 | 10:00 | PC2 CP fail issue after PM | After 2 hrs N2 purging and ran 15 nitride wafers, CP passed. | 2021-07-02 | 12:00 | 2
UNT02 | PM | 2021-09-21 | 9:00 | MF APM | MF APM & SMIF PM done. Cleaned LL chambers and transfer chambers. Tool released for seasoning and QC. | 2021-09-21 | 12:00 | 3
UNT02 | CM | 2021-12-10 | 9:30 | SMIF B unclamp issue during unloading sequence | Found motor base vibration during cassette elevator up position due to motor bush degraded. Temporarily arrested motor vibration and issue solved. SMIF B released for production. | 2021-12-10 | 16:00 | 6.5
UNT02 | CM | 2021-12-14 | 9:30 | PC1 pressure fault alarm | PC1 pressure fault alarm due to APC assembly gear teeth degraded. Replaced gear with motor in the APC assembly. Done APC position adjustment using controller. Ran 5 wafers seasoning without any issue and monitor chamber pressure stabilized. Chamber released for QC. | 2021-12-23 | 11:00 | 217.5
UNT02 | CM | 2021-12-16 | 9:30 | SMIF B unclamp issue during unloading sequence | Replaced elevator motor bushes and handling check done. SMIF B released for production. | 2021-12-16 | 11:30 | 2
UNT02 | CM | 2021-12-17 | 10:00 | SMIF B hang issue during unloading | Adjusted protrude sensor(Crash prevention sensor detects cassette edge instead of slide out wafers from cassette). Handling check done and released to production. | 2021-12-17 | 11:00 | 1
UNT02 | CM | 2022-03-14 |  | Backup | HDD backup failed. Bootup tool with same original HDD and tool recovered without any issue. All parameters and recipe files backup done using FD and able to copy to system. Gas line purging done. Temp ramp down done. | 2022-03-14 |  | 0
UNT02 | CM | 2022-03-15 |  | Dry pumps oil replacement | Done | 2022-03-15 |  | 0
UNT02 | CM | 2022-03-24 |  | Tool power up | All the dry pumps power up done | 2022-03-24 |  | 0
UNT02 | CM | 2022-03-25 |  | Tool power up | Tool power up done and initialize done. SMIF initialized. All chambers pump down done. | 2022-03-25 |  | 0
UNT02 | CM | 2022-03-28 |  | Tool power up | PC1 chiller temp out of range. Swapped PT sensors, both able to read temp. Removed temp controller and hand over to SCL for repair. | 2022-03-28 |  | 0
UNT02 | PM | 2022-04-19 | 10:00 | PC2 RF due PM | PM done. Swapped process kits with cleaned kits. Replaced consumables. Post PM recovery done. Chamber released for QC. | 2022-04-20 | 16:00 | 30
UNT02 | PM | 2022-04-21 | 9:00 | SAPM | SAPM done. SMIF PM done. Tool released for QC. | 2022-04-21 | 11:00 | 2
UNT02 | CM | 2022-06-29 |  | C/C dry pump warning | C/C Dry pump warning in tool display after change from IPX to EPX pump(Aug 2020). Pump side controller no warning signal found. Checked with EPX pump output signals 25 pin D connector and tool interface controller board signals 9 pin D connector, found warning signal pin configuration was as per IPX pump. Soldering done as per EPX pump pin configuration in 25 pin connector, warning signal disappeared | 2022-06-29 |  | 0
UNT02 | CM | 2022-07-13 |  | PC1 chiller temp controller reads out of range. | New temperature controller received from SCL SDC25 and installed in chiller. Controller is not communicating with chiller HMI. | 2022-07-19 |  | 144
UNT02 | CM | 2022-07-01 | 11:00 | PC1 chiller temp controller reads out of range. | Replaced Temperature controller SDC20 with AC volt config. Tapped 220volt from chiller power distribution. Configured setup parameters. Tested it was able to communicate with tool HMI. Tool released for qualification. | 2022-07-19 | 16:00 | 437
UNT02 | CM | 2022-08-25 | 12:00 | Transfer chamber unable to reach base pressure | UNT02 transfer chamber unable to reach base pressure issue. Isolated and found dry pump is faulty. Replaced with new dry pump and pump down, reached base pressure. Tool released for QC. | 2022-08-26 | 16:00 | 28
UNT02 | CM | 2022-09-29 | 15:00 | SMIF B hang issue during unloading sequence | Found protrude sensor alignment out. Alignment done on both transmitter and receiver sensors. Handling check done and tool released. | 2022-09-30 | 11:00 | 20
UNT02 | CM | 2022-10-03 | 10:00 | APM | APM done. SMIF PM done. Tool released. | 2022-10-03 | 13:00 | 3
UNT02 | CM | 2022-12-16 | 9:00 | PC1 Power failure +12V and +24V | 12V power supply repaired and 24V power supply replaced. Installed in tool and chamber recovered. Chamber released for seasoning and QC. | 2022-12-17 | 17:00 | 32
UNT02 | CM | 2023-02-09 | 9:30 | PC2 Pressure control timeout alarm | PC2 Pressure fault alarm Found APC throttle valve gear teeth degraded. Swapped the same with PC1 and PC2 recovered. APC calibration and chamber purging done. QC Passed and chamber released to production. PC1 upgraded with new throttle valve kit and verified open close position. Chamber leak check pass at 0.2mtorr. Performed APC calibration using CPA software and ran 5 wafers seasoning without any issue. Verified 100mtorr process recipe and the pressure is stable. Chamber released for more seasoning and QC. QC Passed and chamber released to production. | 2023-02-13 | 17:30 | 104
UNT02 | PM | 2023-04-04 | 10:00 | Semi Annual PM | Semi Annual PM done and SMIF PM done. Tool released for post PM Qual. | 2023-04-04 | 12:30 | 2.5
UNT02 | CM | 2023-06-25 | 9:00 | PC2 CP fail | Chmaber purged for 2 hrs and released for QC. CP passed. | 2023-06-25 | 11:00 | 2
UNT02 | CM | 2023-08-10 |  | TMP Cooling water flow dropped | Verified flow rate was below 3 ltr/min the spec . Adjusted and alarm was cleared. Tool released to monitor. | 2023-08-10 |  | 0
UNT02 | CM | 2023-08-23 | 15:30 | PC1 wall and upper electrode temprature alarm | Checked heater wires and verified heater sensors, no abnormalities were found. Reboot the system and alarm cleared. But during initialize tool gave “gap motor alarm”. Found 5V power supply output was low at 4.8V. Tuned voltage to 5.1V. Chamber able to initialize but not able to reach base pressure. Upon further check, found nupro valve internal leak were 250mTorr baratron connected. Since we don’t have nupro valve, we bypassed the port and used the spare port. Chamber leak check passed and ran 5 wafers seasoning without any issue. Tool released seasoning and QC. | 2023-08-25 | 14:30 | 47
UNT02 | CM | 2023-08-31 |  | PC1 wall and upper electrode temprature alarm | Verified 5v power supply voltage dropped from 5.1v to 4.9v. Replaced new power supply verifed voltage is 4.98v and adjusted to 5.1v. Chamber recovered and released to monitor. | 2023-08-31 |  | 0
UNT02 | CM | 2023-09-02 |  | SMIF B Hang | During unloading lot hang in smif B. Initialized and lot recovered didnt found any abnormalities. Ran few cycling without any issue. Release to monitor. | 2023-09-02 |  | 0
UNT02 | CM | 2023-09-18 | 14:00 | HDD backup | Tool backup and clone HDD completed successfully. MF and PC1 released for QC. | 2023-09-19 | 14:00 | 24
UNT02 | PM | 2023-09-19 | 14:00 | PC2 RF due PM, lifter pin replacement and MF APM | No abnormalities found on the lift pin during PM. But observed lift pin screw head rounded and not tighten fully. Also found one of the screws is short. Bought screws from local market and replaced all 4 along with new lift pin. Process kit and consumables replaced. Turn ON chiller and no leak observed. Performed hands off verification and post PM recovery. Ran 3 wafers seasoning without any issue. Chamber released for QUAL. MF APM along with SMIF PM completed. | 2023-09-21 | 14:00 | 48
UNT02 | CM | 2023-09-22 | 16:00 | LLB convectron gauge pressure reading drift | Adjusted voltage from 5.1V to 4.32V in atmosphere condition. LLB released. | 2023-09-22 | 17:00 | 1
UNT02 | CM | 2023-10-13 | 11:00 | SMIF-B Cassette elevator hang during unloading. | Replaced crash prevention sensor transmitter side. Performed hands off and cycling without any issue. SMIF-B released for production | 2023-10-13 | 17:00 | 6
UNT02 | CM | 2023-10-16 |  | Cassette chamber 2 CP failed. 0.5 count high 22. | Cleaned C/C2 and CP passed @ delta 2. | 2023-10-16 |  | 0
UNT02 | CM | 2023-10-19 | 15:00 | PC2 CP failed. | Performed mech CP found CC2 CP failed. Performed different simulation and all failed. Found pumping and venting speed abnormal. Further checking found convectron gauge drifted and beyond tuneable range. Convectron gauge Swapped from PC1 and performed mech CP, passed. | 2023-10-25 | 17:00 | 146
UNT02 | CM | 2023-11-24 | 21:00 | SMIF B hang issue during Unloading. | Found SMIF base trifted. Alginment done and handsoff verification completed. Released for production. | 2023-11-28 | 12:00 | 87
UNT02 | CM | 2024-01-10 | 14:30 | System and Data image backup | System and Data image backup completed. | 2024-01-10 | 16:30 | 2
UNT02 | CM | 2024-02-28 | 20:00 | SMIF B hang while unloading | Crash prevention sensor position optimized. Performed hands off verification and cycling without any issue. SMIF B released for production | 2024-02-29 | 10:00 | 14
UNT02 | CM | 2024-03-04 | 8:00 | PC2 24V power supply failure | 24V power supply found faulty. 24V power supply replaced. Installed in tool and chamber recovered. Ran 3 wafers cycling without any issue. Chamber released for seasoning and QC. | 2024-03-04 | 11:30 | 3.5
UNT02 | PM | 2024-04-01 | 10:00 | Mainframe Semi Annual PM | Mainframe Annual PM and SMIF PM completed. Tool released for QC. | 2024-04-01 | 12:30 | 2.5
UNT02 | CM | 2024-05-09 | 9:00 | PC2 Hang | Problem: PC2 hang during production and PC2 gate open time out error. Action: Verified 5V power supply output was low at 4.98V. Tuned voltage to 5.15V. I/O Board not installed alram trigrred and DIO board swapped from PC1 alarm was cleared. Performed APC calibration. Tool released to QC and QC passed. Tool released to production. | 2024-05-09 | 13:00 | 4
UNT02 | CM | 2024-05-10 | 17:00 | PC2 Hang | Process chamber 2 hang during production lot. To recover the wafer, lot aborted and tool reboot. After reboot, during tool initialize found wafer broken in cassette chamber 2. Cassette chamber broken wafers debris cleared and chamber cleaned. 10 wafers found broken out of 25 wafers lot. Cassette chamber 2 down for further checking. Hard disk replaced as suspected there may be parameters malfunctioned during tool hang. Ran Seasioning without any issue. Tool released for QC and QC passed. Tool released to monitor. | 2024-05-11 | 9:00 | 16
UNT02 | PM | 2024-05-27 | 10:00 | PC1 Time based PM | PC1 Time based PM. Chamber opened and inspected no abnormalities were found. Ceramic sleeve found damaged and the same has been replaced. Convectron gauge replaced due to faulty. Performed chamber wipe down and leak check rate, passed. Chamber released for QC | 2024-05-27 | 15:00 | 5
UNT02 | CM | 2024-07-09 | 10:00 | CC1 Gate valve replaced | Cassette chamber 1 gate valve replaced. After replace, transfer chamber unable to pump down to base pressure. Hook up the helium leak detector and found leak from the gate valve side. Removed the gate valve and inspect, found bellow got dent which is causing the leak. Replaced the bellow from the old gate valve. Installed and transfer chamber able to pump down to base pressure. Performed leak rate on both load locks and transfer chamber, passed. Ran seasoning and CP on PC1 from both load locks passed. CP Delta 9 and 2, respectively. Tool released for seasoning and QC. | 2024-07-10 | 10:30 | 24.5
UNT02 | CM | 2024-07-18 | 12:30 | PC2 Hang | PC2 hang with wafer inside. Wafer recovered without any issue. Noticed lots ran in parallel mode Changed back to serial mode and tool released to monitor. | 2024-07-18 | 13:45 | 1.25
UNT02 | CM | 2024-07-24 | 10:00 | Process chamber-2 RF DUE PM 254/250 RF Hrs. | Process kits and consumables replaced. Performed gap calibration and optimized lifer pin susceptor position. Atmosphere pressure convectron gauge replaced due to found faulty. Post PM recovery completed and ran 3 wafers seasoning without any issue. Chamber released for QUAL. CP failed 3x. Isolated and found CP failed issue due to upper electrode. Replaced new upper electrode and CP Passed. | 2024-07-25 | 11:00 | 25
UNT02 | CM | 2024-07-31 | 18:30 | PC2 Temp stablization error | Dry air flow valve adjusted, and temp is stable. release to monitor. | 2024-08-01 | 9:30 | 15
UNT02 | CM | 2024-08-02 | 15:00 | PC2 hang | Tool rebooted and wafer recovered. PC2 Temp board swap from PC1 due to upper temp unsatble issue. | 2024-08-02 | 16:00 | 1
UNT02 | CM | 2024-08-09 | 15:00 | PC2 upper electrode chiller refill | Drained the chiller circulating liquid and refilled new 9 bottles of galden HT135 Resumed the flow and ramp up the temperature. Chamber released for QC | 2024-08-09 | 17:00 | 2
UNT02 | CM | 2024-08-12 | 15:00 | PC2 Upper electrode temperature stabilization issue. | Replaced old upper electrode and ran 17 wafers VIA-DOE-13 recipe. Temperature back to base line. Max temperature is 64.2 degree. Chamber released to QC. QC passed. | 2024-08-13 | 11:00 | 20
UNT02 | CM | 2024-08-17 | 15:30 | PC2 hang | Wafer recovered. Replaced 24V power supply. Tool recovered and ran 2 wafers on both chamber. Tool released for QC. | 2024-08-17 | 18:00 | 2.5
UNT02 | CM | 2024-08-26 | 17:00 | Tool power trip | Checked breakers and EMO no abnormalities were found. Tool power ON. Able to boot up and tool recovered. Encountered PC2 cathode chiller temperature controller out of range PV -130C Swapped with PC1 and confirmed PC2 controller is faulty. PC2 released for QC. QC Passed. PC1, New temperature controller given by SCL installed but having communication issue. Same model temperature controller installed in the chiller, Issue resolved. Temperature reached setpoint and ran 3 wafers on both chambers without any issue. PC1 chamber released for QC | 2024-09-03 | 10:00 | 185
UNT02 | PM | 2024-09-24 | 9:30 | Mainframe Annual PM | Mainframe Annual PM completed and SMIF PM completed. Tool released for QC. | 2024-09-24 | 12:00 | 2.5
UNT02 | CM | 2024-10-08 | 8:00 | PC2 pressure control time out as gate open. | Lot auto recovered. Manually controlled PC2 pressure able to achieve. Ran 3 wafers seasoning without any issue. chamber released to monitor. | 2024-10-08 | 9:00 | 1
UNT02 | CM | 2024-10-14 | 9:00 | Pre aligner timeout error | Pre aligner lifter speed optimized and released to monitor. | 2024-10-14 | 9:30 | 0.5
UNT02 | CM | 2024-11-14 | 9:00 | PC2 gate valve open timeout alarm | Noticed that APC response delay during pressurize chamber for gate open. Performed APC calibration. Ran 3 wafers seasoning without any issue. Chamber released. | 2024-11-14 | 10:00 | 1
UNT02 | CM | 2024-11-21 | 12:30 | PC2 hang during production | Reboot the tool and recovered wafer. Tool released for production. | 2024-11-21 | 13:30 | 1
UNT02 | CM | 2024-12-03 | 12:00 | PR ash rate failed x6 times | UNT02 PC2 Ash rate fail issue. Performed MFC flow verification, RF verification, chamber and MFC leak check, ran more seasoning and the Ash rate was still failed. Performed chamber RF PM (133 RF hrs) and post PM recovery completed. New upper electrode installed, and this series upper electrode had temperature stability issue with longer recipe. Added CDA cooling above the upper electrode and ran 15 wafers with longer recipe and the max temperature is 64C(set point 60C) Chamber released for post PM qual. PC2 APC upgradation APC upgrade kit installed in tool and calibration done. Ran 5 wafers seasoning without any issue. RF verfication data: SP 1700W, Actual 1644W. | 2024-12-06 | 19:00 | 79
UNT02 | CM | 2025-01-14 | 12:00 | Arm positioning error (error code 2002) in cassette chamber 2 during QC. | Reset the robot controller and alarm remain the same. Checked arm 1&2 timing belt condition and no abnormalities found. Upon further checking found 24V power supply in the robot controller faulty. Replaced the same and ran 100 wafers cycling on both chambers without any issue. Tool released for QC. | 2025-01-17 | 16:00 | 76
UNT02 | CM | 2025-01-27 | 9:00 | Robot Assembley Lubrication. | Robot assembly lubrication done. Transfer chamber and LL cleaning done. Ran cycling 25 wafers on each PC1 and PC2. Tool Released for QC. | 2025-01-27 | 13:00 | 4
UNT02 | CM | 2025-01-31 | 15:00 | Tool power trip | Reboot the tool and found “hard disk read error”. Replaced backup system hard disk and tool recovered. Ran cycling on both chambers without any issue. Tool released for QC. | 2025-01-31 | 18:30 | 3.5
UNT02 | CM | 2025-02-19 | 9:00 | To do- HDD system backup,Floppy Data backup and robot controller Cooling fan change | System and Data backup done Robot controller Cooling fan changed | 2025-02-19 | 13:00 | 4
UNT02 | CM | 2025-02-28 | 10:00 | Tool power trip | Reboot the tool and found “hard read error”. Replaced backup system hard disk and tool recovered. Ran cycling on both chambers without any issue. Tool released for QC. | 2025-02-28 | 14:00 | 4
UNT02 | CM | 2025-03-03 | 9:30 | To do- HDD system and data backup | System and Data backup done (Image and Clone) Image backup for Data HDD validation done. | 2025-03-03 | 17:00 | 7.5
UNT02 | CM | 2025-03-05 | 9:30 | CC2 Slit Door minor leak | Gate valve assembly replaced. Mechanical CP passed and released the tool. | 2025-03-05 | 17:00 | 7.5

## SUMMARY
Count of DOWN CATEGORY | Column Labels
| 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | Grand Total
Row Labels
CM | 6 | 17 | 19 | 12 | 12 | 19 | 7 | 92
PM | 1 | 3 | 2 | 2 | 2 | 3 |  | 13
Grand Total | 7 | 20 | 21 | 14 | 14 | 22 | 7 | 105